## Sheet1
Regression and resampling methods
		friday 4th	saturday 5th	sunday 6th	monday 7th	tuesday 8th	wednesday 9th	thursday 10th	friday 11th	Deadline
	a) OLS on franke’s function with resampling
	Generate dataset for Franke’s function
	Perform a standard OLS with polynomials in x and y up to 5th order.
	find confidence intervals for b through computing their variance
	compute MSE and R^2 score function
	b) Resampling techniques, adding more complexity
	perform resampling of data by splitting it into test and training sets
	rule of thumb, 2/3 or 4/5 train/test
	implement k-fold cross validation and evaluate MSE for test data
	c) Bias-variance tradeoff
	Show and expand on the mathematical meaning of rewriting the cost function
	Discuss the bias-variance tradeoff as a function of model complexity(plynomial degree) and number of data points [possibly also training/test data]
	ilustrate with fig. Similar to fig. 2.11 Hastie et al. Include analysis of bias and variance for test resutls [curve unlikely to be as smooth]
	d) Ridge regression on Franke function with resampling
	Write own code for Ridge regression either matrix inversion or singular value decomposition eg. as in hw2 – also chapt. 3.4 Hastie et al, eq (3.43) & (3.44)
	Perform the same analysis as with OLS(with the same data and resampling). Now varying the l variable. Study both the dependence on l. and the comparison to OLS.
	Consider the bias-variance tradeoff here as well.
	e) Lasso Regression on Franke function with resampling
	implement lasso regression as with the previous methods on the franke function data with resampling and so on. Use scikitlearn
	critical discussion of methods used. Judge whitch model best fits the data.
	f) introducing real data
	Having tested the methods properly, aquire real data from earthexplorers.gov
	register with the site, select and area and download the data. Then import it into a program.
	g) OLS, Ridge and Lasso regression with resampling
	Use the aquired terrain data and parameterise it using the same polynomials and methods as above. Compare the fit to the data.
	Evaluate which model fits best the data, and present, critically, the data at the end.
	Write a report with abstract, introduction, theory, method, results and conclusion.
	Tell a story through the report. Why are the steps made, how do they relate. Focus on insights.